## Vijay
Capability | Capability Feature | Product Backlog | Release Date | Release Version | Planned Sprint | Revised Sprint | Complete Sprint | Status | Date Identified | Hours | Assignee | Comments
Containerization | Docker Containerization | Docker Installation |  |  | 1 |  | 1 | Done
| Docker Containerization | Docker Image Creation |  |  | 2 |  | 2 | Done
| Docker Containerization | Push Docker Image to Repository |  |  | 2 |  | 2 | Done
| Docker Containerization | Pull Docker Image from repository |  |  | 2 |  | 2 | Done
| Docker Containerization | Create container from docker image |  |  | 2 |  | 2 | Done
| Kubernetes | Kubernetes Installation |  |  | 1 |  | 1 | Done
| Kubernetes | Master & Worker Nodes Configuration |  |  | 1 |  | 1 | Done
| Kubernetes | Container Creation & Deployment |  |  | 2 |  | 2 | Done
| Kubernetes | Service Creation for PODs |  |  | 2 |  | 2 | Done
| Kubernetes | Pull Image from repository |  |  | 2 |  | 2 | Done
| Kubernetes | Deployment of DSDP capabilities | 2020-07-10 |  | 5 | Q2-1 | Q2-1 | Done |  |  | Vijay (100%) | Demo needs to be done
| Kubernetes | Manual scaling of PODs | 2020-06-08 |  | 3 |  | 3 | Done |  |  | Vijay (100%)
| Kubernetes | Configure POD using Config Map | 2020-06-12 |  | 3 |  | 3 | Done |  |  | Vijay (100%)
| Kubernetes | Enable Ingress & Configure Rules | 2020-07-10 |  | 4 | Q2-1 | Q2-1 | Done |  |  | Vijay (100%) | Demo needs to be done
| Kubernetes | Metrics Server Deployment | 2020-06-17 |  | 4 |  | 4 | Done |  |  | Vijay (100%)
| Kubernetes | Web UI (Dashboard) | 2020-06-17 |  | 4 |  | 4 | Done |  |  | Vijay (100%)
| Kubernetes | Communication b/w Containers | 2020-06-10 |  | 3 |  | 3 | Done |  |  | Vijay (100%)
| Kubernetes | Resource Based Auto Scaling | 2020-06-09 |  | 3 |  | 3 | Done |  |  | Vijay (100%)
| Kubernetes | Auto Scaling using Custom Rules | 2020-06-08 |  | 3 |  | 3 | Done |  |  | Vijay (100%)
| Kubernetes | Session Handling in PODS | 2020-07-10 |  | 4 | Q2-2 |  | Open |  |  | Vijay (100%)
| Kubernetes | Persistent Logging | 2020-06-16 |  | 4 |  | 4 | Done |  |  | Vijay (100%) | Demo needs to be done
| Kubernetes | Persistent Storage | 2020-07-10 |  | 5 | Q2-2 |  | Open |  |  | Vijay (100%)
| Kubernetes | s | 2020-07-10 |  | 5 | Q2-1 | Q2-1 | Done |  |  | Vijay (100%) | Demo needs to be done
| Kubernetes | Release upgrade and rollback | 2020-06-29 |  | 5 | 6 | 6 | Done |  |  |  | Demo needs to be done
| Kubernetes | Node affinity | 2020-06-24 |  | 5 |  | 5 | Done |  |  |  | Demo needs to be done
| Kubernetes | Inter-pod affinity and anti-affinity
| Kubernetes | Taints and Tolerations | [5 empty] | Open
| Kubernetes | Security in Kubernets
| Kubernetes | Capability Automation Suite Execution and support | 2020-07-17 |  | Q2-2
Security of CDC | Static Analysis | As a developer, I shall run the MobSf and share the findings of the CDC Meet App of both IOS/Android apps
| Accunetix Scanning | As a developer, I shall run the Accunetix on the WebRTC and share the findings . | 2020-07-17 |  | Q2-2 |  |  | Open
| Penetration testing | As a developer, I shall run burp suite and try to do the MIMT & and Replay attack on Web/App interface. | 2020-07-17 |  | Q2-2 |  |  | Open
| SSL Analysis | As a developer, I shall run our domain on SSL labs and share the findings. | 2020-07-17 |  | Q2-2 |  |  | Open
| Infra Security | As a developer, I shall audit the server and check all the security recommendation for the Middleware assessment and share the findings. | 2020-07-17 |  | Q2-2 |  |  | Open
| Nessus Scan | As a developer I shall run the Nessus tool to find out the OS related security patches and share the findings.
| Dyanamic Analysis | As a developer, I shall run the MobSf and share the findings of the CDC Meet App of both IOS/Android apps

## EPIC
S.No | EPIC | List of Task Coverd | Target Sprint | Completed in Sprint
1 | Image Creation independent of properties file modification during its creation and autoscalling of product on the basis of the resources and traffic | 1. Manual Scalling 2. Auto scalling on resource based 3. Auto scalling on TPS or KPI generated by application 4. config map | 3 | 3
2 | Logs availibility as per the operator guidelines and UI for operation to check system behavior. | 1. Persistent Logging 2. Dashboard UI 3. Metric Server | 4 | 4
3 | Whitelisting of soure IP for the genuine traffic and session management | 1. Session Handling in the POD 2. Enable ingress and configure rules. | 4
4 | System upgrdation and maintenance | 1. Persistent storage 2. CronJob scheduling 3. Patch upgrade and rollback steps | 5
5 | Rollout the Containerization in DSDP capabilities one by one. | Deployment of DSDP capabilities | 5